## ACME Sprint Planner & Tracker
Sprint Planning and Tracking | [21 empty] | by Tipsographic.com
Sprint Planning and Tracking
PROJECT TITLE |  | Locker Project | [19 empty] | © 2015-2022 Tipsographic.com
PROJECT MANAGER |  | Shreyash Pawar
COMPANY NAME |  | Simpli Learn | [19 empty] | ► Sprint Backlog with Burndown Chart Template
DATE |  | 2/15/2022 | [19 empty] | ► User Story Template
► More Agile Project Management Templates
PLANNER & TRACKER
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Sprint 5
Sprint 6
TASK | TASK | TASK | AMOUNT OF WORK IN HOURS |  |  | STORY | START | DUE | DURATION | STATUS | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2
ID | NAME | OWNER | ESTIMATE | COMPLETED | REMAINING | POINTS | DATE | DATE |  |  | COMPLETE | M | T | W | T | F | M | T | W | T | F
| SPRINT #1 | Shreyash Pawar | 7 | 7 | 0 | 7 | 31/1/2022 | 2022-04-02 | #VALUE! | Completed | 100%
1 | Analysis Finished | Shreyash Pawar | 1 | 1 | 0 |  | 2021-10-01 | 2021-10-04 | 4 | Completed | 100%
2 | Document Current System | Shreyash Pawar | 1 | 1 | 0 |  | 2021-10-05 | 2021-10-08 | 4 | Completed | 100%
3 | Get All Files Functionality | Shreyash Pawar | 2 | 2 | 0 |  | 2021-10-09 | 2021-10-10 | 2 | Completed | 100%
4 | Add New File Functionality | Shreyash Pawar | 3 | 3 | 0 |  | 2021-10-10 | 2021-10-10 | 1 | Completed | 100%
| SPRINT #2 | Shreyash Pawar | 7 | 7 | 0 | 1 | 2021-10-11 | 2021-11-05 | 26 | Completed | 100%
5 | Delete Existing File Functionality | Shreyash Pawar | 1 | 1 | 0 |  | 2021-10-11 | 2021-10-17 | 7 | Completed | 100%
6 | Search Existing File Functionality | Shreyash Pawar | 2 | 2 | 0 |  | 2021-10-18 | 2021-10-25 | 8 | Completed | 100%
7 | Overwrite Existing File While Adding | Shreyash Pawar | 2 | 2 | 0 |  | 2021-10-26 | 2021-10-30 | 5 | Completed | 100%
8 | Documentation | Shreyash Pawar | 2 | 2 | 0 |  | 2021-10-26 | 2021-11-05 | 11 | Completed | 100%
Note: This spreadsheet is for informational and educational purposes only. Tipsographic makes no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to this spreadsheet. Any reliance you place on such information is therefore strictly at your own risk.